# Renewal Risk Register

Account Alpha renewal  |  Owner: Rowan Mercer

# Operating intent

Use this register at the weekly close review. Status is assessed against the 2026-07-17 decision date; each row has a named action rather than a generic mitigation.

| Risk | Level | Trigger | Mitigation / owner | Due |
| --- | --- | --- | --- | --- |
| Procurement routing starts late | Amber | No route confirmed | Send complete supplier packet; Morgan Hale confirms path. | 2026-07-10 |
| Legal redlines fragment | Amber | Multiple channels | Single tracker; Rowan Mercer consolidates. | 2026-07-13 |
| Sponsor outcome proof weak | Amber | Avery requests more evidence | Review scorecard and adoption plan. | 2026-07-01 |
| Data Connect review expands | Yellow | New material scope | Elliot Park classifies impact; keep commercial scope stable. | 2026-06-26 |
| Signature window compresses | Red | Open material item after 07-15 | Priya Noland executive escalation. | 2026-07-15 |

# Review controls

Rowan updates this register every Tuesday and in daily close-week status. A risk may close only when its evidence is recorded in the mutual action plan.