# Account Beta risk response plan

Customer pack | Target renewal 2026-09-30 | Working plan

# Risk register

Risks are managed as observable operating conditions, not assumptions about the customer.

| Risk | Early signal | Mitigation | Owner |
| --- | --- | --- | --- |
| Adoption plateau | Active teams remain below 85% | Targeted enablement and office hours | Priya |
| Value narrative incomplete | Dana cannot link workflow to operating review | Build baseline-to-outcome readout | Rowan |
| Procurement timing | Cameron has no timeline confirmed | Request process checklist by 2026-08-28 | Rowan |
| Scope expansion premature | Data-connect requested without proof | Gate behind adoption target | Joint team |

# Escalation rule

Escalate internally if a red risk remains unresolved for five business days or threatens the 2026-09-18 paperwork-ready checkpoint.

| Checkpoint | Status definition | Response |
| --- | --- | --- |
| Green | On plan with owner and evidence | Continue cadence |
| Amber | Evidence delayed less than five days | Adjust weekly plan |
| Red | Decision or critical evidence blocked | Executive escalation |