# Account Beta mutual action plan

Customer pack | Target renewal 2026-09-30 | Proposed 12-month term 2026-10-01 to 2027-09-30

# Shared milestones

A practical plan that aligns adoption proof, executive review, and procurement readiness.

| Date | Milestone | Customer owner | Northstar owner |
| --- | --- | --- | --- |
| 2026-08-14 | Validate adoption baseline and success measures | Dana Quill | Priya Noland |
| 2026-08-21 | Complete enablement clinic and scorecard update | Dana delegate | Priya Noland |
| 2026-08-28 | Confirm procurement steps and artifacts | Cameron Vale | Rowan Mercer |
| 2026-09-11 | Review commercial scenarios | Cameron Vale | Rowan Mercer |
| 2026-09-18 | Finalize paperwork-ready decision pack | Dana Quill | Rowan Mercer |
| 2026-09-30 | Target renewal date | Dana Quill | Rowan Mercer |

# Working agreement

Owners update evidence before each weekly planning note; scope or commercial changes are recorded as proposals until approved.

| Cadence | Purpose | Output |
| --- | --- | --- |
| Weekly | Execution review | Updated owners and blockers |
| Biweekly | Sponsor value review | Decision narrative |
| As needed | Procurement working session | Document checklist |