## Portfolio Summary
Summit Vale Advisory ¦ consolidated initiative tracker
Portfolio budget (¥M) | 42.8 | Focus | Lead | Next gate
Committed (¥M) | 42.8 | Client Alpha Phase 1 | Avery Calder | 15 Jul
Forecast (¥M) | 42.6 | Client Beta Phase 2 | Nina Solberg | 17 Jul
Remaining (¥M) | 0.2 | Finance integration | Theo Mercer | 18 Jul
Model status | PASS | Portfolio control | Keiko Ward | 20 Jul

## Initiatives
Initiative | Phase | Owner | Status | Approved ¥M | Forecast ¥M | Variance ¥M | Next gate
Client Alpha | Phase 1 | Avery Calder | In progress | 18 | 18.7 | 0.7 | Synthesis review
Client Beta | Phase 2 | Nina Solberg | In progress | 12.6 | 12.1 | -0.5 | Hypothesis test
Finance controls | Portfolio | Theo Mercer | At risk | 5 | 5.4 | 0.4 | Control design
Staffing | Portfolio | Keiko Ward | In progress | 4.2 | 4 | -0.2 | Weekly plan
Contingency | Portfolio | Avery Calder | Planned | 3 | 2.4 | -0.6 | Steerco

## Risks
Risk | Likelihood | Impact | Owner | Mitigation | Status
Data reconciliation delay | Medium | High | Theo Mercer | Daily reconciliation | Open
Decision latency | Medium | Medium | Avery Calder | Pre-wire gates | Open
Capacity overlap | Low | High | Keiko Ward | Hold capacity | Monitored
Scope drift | Medium | Medium | Nina Solberg | Question log | Open

## Controls
Control | Result | Note
Approved total tie | PASS | Initiatives match portfolio ceiling
Forecast total tie | PASS | Dashboard matches initiative forecast
No negative remaining | PASS | Portfolio headroom is non-negative
Model status | PASS | PASS required