# Question log

Working draft for synthesis, decision sequencing, and finance controls

| Client | Client Alpha | Date | 13 Jul 2026 |
| --- | --- | --- | --- |
| Engagement | Phase 1 | Status | Working draft |

# Purpose and use

This log turns open questions into an explicit decision queue for the Client Alpha Phase 1 team. It is deliberately practical: questions are framed so that a working session can close them, escalate them, or convert them into a tracked assumption. The log links to the broader Summit Vale Advisory portfolio, where Finance is managing against a ¥42.8M budget and Client Beta Phase 2 is progressing in parallel.

## Operating rules

Use evidence already available to the workstream before requesting new analysis.

Name one accountable owner and one decision date for each material question.

Escalate only questions that change the Phase 1 recommendation, spending profile, or portfolio trade-off.

Record a provisional answer when a gate cannot wait; tag the assumption for revalidation.

# Active decision queue

| Question | Why it matters | Owner | Due | Path |
| --- | --- | --- | --- | --- |
| Which Alpha workstream has the clearest measurable value case? | Sets synthesis emphasis and evidence threshold. | Avery Calder | 15 Jul | Evidence review |
| What control evidence is needed before Finance approves the next release? | Protects the Phase 1 budget envelope. | Nina Solberg | 16 Jul | Finance huddle |
| Where do Alpha and Beta require the same specialist capacity? | Avoids portfolio conflict in Phase 2. | Keiko Ward | 16 Jul | Staffing plan |
| What data quality threshold is sufficient for the steering recommendation? | Prevents analysis from expanding without a decision benefit. | Theo Mercer | 17 Jul | Data review |
| Which decisions need client confirmation versus team judgment? | Clarifies governance and meeting design. | Avery Calder | 17 Jul | Steerco pre-wire |

# Question details and working hypotheses

## Value case

The leading candidate should show an observable financial or operating outcome, a manageable implementation dependency, and a credible owner. Initial evidence favors a focused control-and-decision workflow rather than a broad transformation claim.

## Finance controls

Nina will define the minimum evidence pack: approved scope, forecast-to-plan bridge, named decision owner, and any exception rationale. The goal is a lightweight gate that preserves pace without weakening budget discipline.

## Data readiness

Theo will classify inputs as decision-ready, directional, or unavailable. Directional inputs may inform a hypothesis but should not be used as the sole basis for a spending commitment.

## Portfolio capacity

Keiko will test specialist overlap across Alpha Phase 1 and Beta Phase 2 before the weekly staffing plan is locked. Any shortage should be treated as a portfolio sequencing issue, not a local scheduling problem.

# Escalation triggers

Forecast movement of more than ¥0.5M from the approved Alpha envelope.

A decision gate slips beyond 17 July without a documented provisional answer.

A shared specialist is committed above available weekly capacity.

Evidence conflicts materially with the current recommendation.

# Decision log and next cadence

At each daily working session, the team should review only questions due within the next three business days, new evidence that changes an existing answer, and exceptions requiring an Alpha–Beta portfolio trade-off. Closed questions remain in the log with a concise answer, evidence reference, and follow-up owner so the synthesis can be audited without reconstructing meeting history.

| Cadence | Participants | Output | Accountable |
| --- | --- | --- | --- |
| Daily 20-minute review | Avery, Nina, Theo, Keiko | Updated question queue | Avery Calder |
| Finance gate | Nina + Avery | Control evidence pack | Nina Solberg |
| Weekly portfolio check | All leads | Alpha/Beta capacity and spend view | Keiko Ward |
| Steering pre-wire | Avery + client lead | Decision-ready narrative | Avery Calder |

# Draft conclusion

The immediate priority is to close the five active questions in decision order, not in analytical order. This preserves the Alpha Phase 1 pace, protects the Finance anchor, and keeps Client Beta Phase 2 linked through an explicit view of shared capacity and control dependencies.