## Slide 1
SUMMIT VALE ADVISORY
Decision pack: approve the Phase 2 operating reset
Client Beta | Phase 2 | 13 July 2026
Engagement team: Avery Calder · Nina Solberg · Theo Mercer · Keiko Ward
Portfolio linkage: Client Alpha Phase 1 Finance budget ¥42.8M
Notes: [Sources]
Synthetic internal analysis; no external sources.

## Slide 2
SUMMIT VALE ADVISORY / CLIENT BETA PHASE 2
Approve a 12-week reset with three gated decisions
13 JUL 2026 • Avery Calder · Nina Solberg · Theo Mercer · Keiko Ward
2
¥18M
cash release by Q4
92%
service protected in pilot
3 gates
SteerCo approvals needed
Recommendation
Approve flex capacity, inventory reset, and supplier escalation as one linked package.
Decision and owner alignment required at the next operating review.
Notes: [Sources]
Synthetic internal analysis; no external sources.

## Slide 3
SUMMIT VALE ADVISORY / CLIENT BETA PHASE 2
Decision value by option (¥M)
13 JUL 2026 • Avery Calder · Nina Solberg · Theo Mercer · Keiko Ward
3
Chart: 
| Flex capacity | Inventory reset | Supplier recovery
Decision value by option (¥M) | 6 | 7 | 5
¥18M
cash release by Q4
Evidence interpretation
The combined package is materially stronger than any stand-alone intervention.
Synthetic internal analysis; no external sources. Metrics are illustrative management estimates.
Notes: [Sources]
Synthetic internal analysis; no external sources.

## Slide 4
SUMMIT VALE ADVISORY / CLIENT BETA PHASE 2
The operating plan assigns a clear owner to each control point
13 JUL 2026 • Avery Calder · Nina Solberg · Theo Mercer · Keiko Ward
4
Action | First deliverable | Accountable lead | Timing
Approve flex capacity | Second-shift pilot at Cell 4 | Keiko Ward | 13 Jul
Approve buffer reset | Release non-critical stock only | Nina Solberg | 20 Jul
Authorize escalation | Recover critical supplier commits | Theo Mercer | 20 Jul
Governance: Keiko Ward chairs a 30-minute weekly operating review; escalate only decisions that alter customer service, capital, or supplier commitments.
Notes: [Sources]
Synthetic internal analysis; no external sources.