## Slide 1
SUMMIT VALE ADVISORY
Implementation roadmap: make the reset irreversible in 12 weeks
Client Beta | Phase 2 | 13 July 2026
Engagement team: Avery Calder · Nina Solberg · Theo Mercer · Keiko Ward
Portfolio linkage: Client Alpha Phase 1 Finance budget ¥42.8M
Notes: [Sources]
Synthetic internal analysis; no external sources.

## Slide 2
SUMMIT VALE ADVISORY / CLIENT BETA PHASE 2
Implementation roadmap: make the reset irreversible in 12 weeks
13 JUL 2026 • Avery Calder · Nina Solberg · Theo Mercer · Keiko Ward
2
12 weeks
to operating handover
3 waves
mobilize, pilot, scale
24 owners
trained in new cadence
Recommendation
Use a wave-based rollout: prove at the constraint first, then scale only what holds.
Decision and owner alignment required at the next operating review.
Notes: [Sources]
Synthetic internal analysis; no external sources.

## Slide 3
SUMMIT VALE ADVISORY / CLIENT BETA PHASE 2
Implementation readiness by week (%)
13 JUL 2026 • Avery Calder · Nina Solberg · Theo Mercer · Keiko Ward
3
Chart: 
| W1 | W3 | W5 | W7 | W9 | W12
Implementation readiness by week (%) | 20 | 38 | 55 | 68 | 82 | 95
12 weeks
to operating handover
Evidence interpretation
Readiness must precede scale; no sitewide rollout before the week-six control review.
Synthetic internal analysis; no external sources. Metrics are illustrative management estimates.
Notes: [Sources]
Synthetic internal analysis; no external sources.

## Slide 4
SUMMIT VALE ADVISORY / CLIENT BETA PHASE 2
The operating plan assigns a clear owner to each control point
13 JUL 2026 • Avery Calder · Nina Solberg · Theo Mercer · Keiko Ward
4
Action | First deliverable | Accountable lead | Timing
Mobilize | Confirm owners and standards | Nina Solberg | W1
Pilot | Prove Cell 4 routines | Avery Calder | W2–6
Handover | Certify daily management | Keiko Ward | W7–12
Governance: Keiko Ward chairs a 30-minute weekly operating review; escalate only decisions that alter customer service, capital, or supplier commitments.
Notes: [Sources]
Synthetic internal analysis; no external sources.