## Slide 1
SUMMIT VALE ADVISORY
Supplier performance review: recover reliability through a tiered reset
Client Beta | Phase 2 | 13 July 2026
Engagement team: Avery Calder · Nina Solberg · Theo Mercer · Keiko Ward
Portfolio linkage: Client Alpha Phase 1 Finance budget ¥42.8M
Notes: [Sources]
Synthetic internal analysis; no external sources.

## Slide 2
SUMMIT VALE ADVISORY / CLIENT BETA PHASE 2
Supplier performance review: recover reliability through a tiered reset
13 JUL 2026 • Avery Calder · Nina Solberg · Theo Mercer · Keiko Ward
2
3 suppliers
driving expedite exposure
76%
current OTIF for critical parts
4 wks
to first recovery checkpoint
Recommendation
Put the critical three on weekly recovery plans and qualify fallback for the highest-risk part.
Decision and owner alignment required at the next operating review.
Notes: [Sources]
Synthetic internal analysis; no external sources.

## Slide 3
SUMMIT VALE ADVISORY / CLIENT BETA PHASE 2
Critical supplier OTIF (%)
13 JUL 2026 • Avery Calder · Nina Solberg · Theo Mercer · Keiko Ward
3
Chart: 
| Supplier A | Supplier B | Supplier C | Target
Critical supplier OTIF (%) | 71 | 74 | 76 | 95
3
Suppliers
driving expedite exposure
Evidence interpretation
The reliability gap is concentrated, allowing a focused escalation rather than a broad supplier program.
Synthetic internal analysis; no external sources. Metrics are illustrative management estimates.
Notes: [Sources]
Synthetic internal analysis; no external sources.

## Slide 4
SUMMIT VALE ADVISORY / CLIENT BETA PHASE 2
The operating plan assigns a clear owner to each control point
13 JUL 2026 • Avery Calder · Nina Solberg · Theo Mercer · Keiko Ward
4
Action | First deliverable | Accountable lead | Timing
Launch recovery plans | Capacity and commit validation | Theo Mercer | Week 1
Control releases | Link PO release to confirmation | Nina Solberg | Week 1 onward
Qualify fallback | Approve alternate for Part X-14 | Avery Calder | Weeks 2–8
Governance: Keiko Ward chairs a 30-minute weekly operating review; escalate only decisions that alter customer service, capital, or supplier commitments.
Notes: [Sources]
Synthetic internal analysis; no external sources.