## Milestones
Study Alpha A-24 ¦ Milestone and Budget Model
Milestone | Weeks | Owner role | Deliverable | Release % | Planned cost (USD) | Cumulative cost (USD) | QC gate
Readiness lock | 1–3 | Program lead | Roster + protocol lock | 18% | 12960 |  | Traceability complete
Verification runs | 4–9 | Assay lead | 3 controlled runs | 32% | 23040 |  | CV ≤10%; recovery 90–110%
Quality review | 10–13 | Quality reviewer | Exception closure record | 25% | 18000 |  | No critical issue open
Decision package | 14–16 | Research lead | Internal recommendation | 25% | 18000 |  | Evidence package accepted
Total

## Inputs & Assumptions
Model Inputs & Analytical Acceptance Criteria
Input | Value | Unit | Note
Total planned budget | 72000 | USD | Synthetic internal planning budget
Baseline median | 6.8 | ng/mL | ALPHA-A24-R03 descriptive context
Duplicate CV threshold | 10% | fraction | Must be at or below threshold
Recovery lower bound | 90% | fraction | Inclusive acceptance bound
Recovery upper bound | 110% | fraction | Inclusive acceptance bound
Cohort size | 24 | coded records | OCW-A24-001 through OCW-A24-024

## Budget by Category
Budget by Category
Category | Amount (USD) | Share of total | Rationale
Personnel | 32400 |  | Planning, assay execution, quality review
Assay materials | 18000 |  | Synthetic controls and consumables
Quality documentation | 10800 |  | Review, reconciliation, evidence assembly
Dissemination package | 10800 |  | Figure, checklist, internal packet
Total