# Research Strategy: Study Alpha A-24

Approach, controls, milestones, and decision framework

| Applicant | Orchid Cellworks |
| --- | --- |
| Protocol and run | OCW-BIO-017 / ALPHA-A24-R03 |
| Baseline observation | Synthetic median: 6.8 ng/mL |
| Scope | Fictional coded cohort A-24; 24 synthetic records |

# Significance

A translational program benefits when analytical evidence is structured before decisions are made. Study Alpha addresses this need with a narrow, controlled test: whether a locked assay workflow can meet precision and recovery thresholds while producing reviewable documentation.

# Innovation

The strategy couples predeclared acceptance criteria with a milestone-funded workplan. Rather than treating quality review as a closing activity, each phase creates a reviewable artifact and a documented decision point.

# Approach

Phase 1 — readiness (weeks 1–3). Confirm the synthetic coded roster, reagent traceability record, and protocol version. Phase 2 — verification (weeks 4–9). Perform planned confirmation runs and calculate duplicate CV and recovery. Phase 3 — review (weeks 10–13). Reconcile deviations, confirm acceptance status, and prepare an evidence narrative. Phase 4 — decision package (weeks 14–16). Submit an internal recommendation with actions, owners, and budget reconciliation.

## Quality plan

Precision criterion: duplicate CV ≤10%.

Recovery criterion: 90–110%.

Signal context: baseline median 6.8 ng/mL is descriptive, not a clinical endpoint.

Exception control: any failed criterion is recorded, investigated, and closed before recommendation.

## Analysis and interpretation

For each synthetic identifier, the two planned measurements will be summarized as a mean, duplicate CV, and recovery percentage. Run-level summaries will show median response and the count of records within each threshold. A pass requires complete evidence and no unclosed critical quality issue; a conditional outcome triggers a scoped corrective-action plan.

# Risks and alternatives

| Risk | Mitigation | Decision trigger |
| --- | --- | --- |
| Precision drift | Repeat controlled run; inspect handling record | CV >10% |
| Recovery excursion | Confirm control preparation; rerun affected set | Outside 90–110% |
| Documentation gap | Reconcile source log before review | Traceability incomplete |

# Milestones and dissemination

The milestone/budget model maps funds to the same gates described here. The final internal packet will include this strategy, specific aims, a workplan figure, review actions, and a checklist. All deliverables remain fictional corpus artifacts.

## 16-week milestone timeline

| Window | Milestone & evidence | Budget release |
| --- | --- | --- |
| Weeks 1–3 | Readiness lock: coded roster, protocol OCW-BIO-017, and calculation template reconciled. | 18% • $12,960 |
| Weeks 4–9 | Three controlled verification runs; duplicate CV and recovery review recorded. | 32% • $23,040 |
| Weeks 10–13 | Quality review: exceptions investigated, corrective actions closed, evidence reconciled. | 25% • $18,000 |
| Weeks 14–16 | Decision package: strategy, figure, checklist, action log, and budget closeout assembled. | 25% • $18,000 |

## Closeout and decision ownership

| Accountable role | Closeout responsibility | Required decision |
| --- | --- | --- |
| Assay lead | Confirms run record and duplicate-CV evidence for ALPHA-A24-R03 follow-up. | Accept or escalate precision evidence |
| Quality reviewer | Closes recovery exceptions against the 90–110% acceptance window. | Confirm no critical issue remains open |
| Research lead | Reconciles the $72,000 milestone budget and evidence package. | Issue go / conditional / hold recommendation |

## Dissemination deliverables

Internal review PDF documenting evidence disposition and required actions.

Formula-driven milestone and budget model, plus the 16-week workplan figure.

Final closeout criterion: complete traceability, CV ≤10%, recovery 90–110%, and no unclosed critical quality issue.