# Specific Aims: Study Alpha A-24

A criterion-driven translational assay verification plan

| Organization | Orchid Cellworks |
| --- | --- |
| Protocol | OCW-BIO-017 |
| Run context | ALPHA-A24-R03 baseline: median 6.8 ng/mL |
| Study population | 24 synthetic coded records: OCW-A24-001…OCW-A24-024 |

# Overall objective

The objective is to establish whether the Study Alpha workflow can generate a reproducible, well-documented synthetic assay evidence package under a fixed protocol and predeclared acceptance criteria. The central premise is that traceability plus quantitative QC gates will make the internal decision process auditable and efficient.

# Aim 1 — Establish analytical repeatability

Execute three verification runs using the locked workflow and compare duplicate measurements within each coded record. Success is defined as duplicate CV ≤10% across the planned assessment set and a complete run-level audit trail.

# Aim 2 — Demonstrate recovery control

Assess recovery against the predefined 90–110% window while documenting any exception, rerun rationale, and corrective action. Success is a closed quality record with no unresolved critical deviation.

# Aim 3 — Produce a decision-ready evidence package

Integrate the verification outputs into a concise strategy report, milestone/budget model, workplan figure, and internal review record. Success is a time-bounded recommendation tied directly to the acceptance matrix, not an inference about clinical performance.

# Expected impact

The project will yield a disciplined, reusable method for moving a synthetic assay signal from exploratory observation to a transparent internal decision. The approach is intentionally bounded: it supports analytical readiness planning and does not use real subjects, samples, or external data.

| Aim | Readout | Gate |
| --- | --- | --- |
| 1 | Duplicate precision | CV ≤10% |
| 2 | Recovery | 90–110% |
| 3 | Evidence package | Internal review acceptance |