## Slide 1
JUNIPER WORKS | PRODUCT ALPHA Q3
01 / 05
Q3 activation pre-read
Decision: approve the operating path to M-27
Target adoption: 18.4% → 26.0%
M-27 | 2026-09-18 | Owner: PM-local-08

## Slide 2
DECISION CONTEXT
02 / 05
A path to close the 7.6-point gap
Adoption must rise 7.6 points by M-27. The plan creates a common metric, tests a lifecycle intervention, and reviews movement weekly.
18.4%
current adoption baseline
26.0%
M-27 objective

## Slide 3
OPERATING PATH
03 / 05
Three moves create a weekly learning loop
01
Define
ACT-27A · 2026-07-20
Publish one activation event dictionary.
02
Test
ACT-27B · 2026-07-27
Set message, holdout, and frequency cap.
03
Steer
ACT-27C · weekly from 2026-08-03
Review movement, segments, and blockers.

## Slide 4
READINESS
04 / 05
The final gate is one week before M-27
ACT-27A
Metric definition
2026-07-20
ACT-27B
Experiment brief
2026-07-27
ACT-27D
Readiness review
2026-09-11
M-27
Objective date
2026-09-18
Decision rule: do not read experiment impact until the event dictionary and holdout are confirmed.

## Slide 5
DECISION
05 / 05
Approve the activation operating path
Approve ACT-27A through ACT-27D as the Q3 path to 26.0% adoption by M-27.
Immediate next step
Publish the activation event dictionary by 2026-07-20.
Supporting local working set: roadmap memo, action tracker, sync notes, pinned-file index, and synthetic offline trace.