## Slide 1
Q3 ROADMAP REVIEW
Product Alpha
ships the adoption
learning loop.
Juniper Works | 2026-07-13
1,240 synthetic workspaces • adoption target: 18.4% → 26.0%
M-27 • 2026-09-18
JUNIPER WORKS / PRODUCT ALPHA Q3
01

## Slide 2
M-26 capacity is the roadmap's only active constraint.
Role owners hold their handoffs; Product Management owns the M-27 decision.
ID
DATE
MILESTONE
ROLE OWNER
STATUS
M-24
07/24
Discovery closeout
Product Management
COMPLETE
M-25
08/07
Design + instrumentation ready
Design + Data
ON TRACK
M-26
08/28
Beta cohort enabled
Engineering + CS
AT RISK
M-27
09/18
Q3 adoption decision
Product Management
PLANNED
JUNIPER WORKS / PRODUCT ALPHA Q3
02

## Slide 3
The Q3 goal is a 7.6-point adoption gain by M-27.
Chart: 
| Baseline 2026-07-13 | Target M-27 2026-09-18
Adoption | 18.4 | 26
+7.6 points
required to move from 18.4% to 26.0% adoption
M-26 is the gating handoff
Entitlement capacity confirmation remains at risk.
Measure through the decision
DEP-04 keeps the adoption readout attached to M-27.
JUNIPER WORKS / PRODUCT ALPHA Q3
03

## Slide 4
Resolve the dependency chain before the M-27 decision.
DEPENDENCY
TARGET
ACCOUNTABLE ROLE
STATUS
DEP-01 Event naming review
M-25
Data
ON TRACK
DEP-02 Entitlement service capacity confirmation
M-26
Engineering
AT RISK
DEP-03 Beta onboarding playbook
M-26
Customer Success
ON TRACK
DEP-04 Adoption metric readout
M-27
Product Management
PLANNED
Decision ask
Engineering confirms DEP-02 capacity before the beta cohort; PM then locks the M-27 readout agenda.
JUNIPER WORKS / PRODUCT ALPHA Q3
04