## Slide 1
PRODUCT ALPHA Q3
A focused path to
M-27 adoption
Roadmap review • 2026-07-13
Milestone: 2026-09-18
18.4%
current adoption across 1,240
synthetic workspaces
Juniper Works • Product Alpha Q3 • 2026-07-13
01

## Slide 2
Q3 SIGNAL
The adoption gap is visible—and addressable
Our weekly goal is to move from 18.4% toward 26.0% with a narrower experience, not a larger release.
18.4%
current activated-workspace adoption
26.0%
Q3 operating target
+7.6 pp
gap to close through clearer next actions and visibility
Juniper Works • Product Alpha Q3 • 2026-07-13
02

## Slide 3
RECOMMENDATION
Make M-27 the smallest credible adoption release
Three connected changes solve the most frequent triage signal.
01
Guided setup checklist
Clarifies the next teammate action
02
Weekly adoption pulse
Shows progress against the 26.0% target
03
Empty-state rewrite
Explains the first step without support help
Juniper Works • Product Alpha Q3 • 2026-07-13
03

## Slide 4
SEQUENCING
Cut scope by dependency, not by aspiration
M-27 holds one material risk: the reporting schema must support a stable weekly denominator.
NOW
Jul 13–17
Confirm cohort definition
Finalize empty-state copy
BUILD
Jul 20–Aug 28
Checklist + pulse build
Schema checkpoint
VALIDATE
Sep 1–11
Synthetic cohort review
Support readiness
M-27
Sep 18
Focused release
Weekly readout begins
Juniper Works • Product Alpha Q3 • 2026-07-13
04

## Slide 5
DECISION
Approve the focused M-27 bundle
Today’s choice preserves speed while keeping the Q3 target measurable.
Approve
Guided setup checklist + adoption pulse + empty-state rewrite
Defer advanced CSV export until the reporting schema decision is closed.
Juniper Works • Product Alpha Q3 • 2026-07-13
05