## Slide 1
PRODUCT ALPHA
Q3 release plan
A controlled route from internal learning to guided customer rollout.
Juniper Works | 13 July 2026

## Slide 2
DECISION FRAME
The release earns expansion through evidence, not calendar pressure
1,240 eligible synthetic workspaces; adoption target 18.4% to 26.0%.
CURRENT ADOPTION
18.4%
Q3 TARGET
26.0%
GATE DATE
18 Sep
ELIGIBLE
1,240
Protect customer workflow continuity while Product Alpha changes behavior.
Make support capacity and rollback signals visible before each wave.
Juniper Works | Product Alpha Q3 | 2026-07-13
PLAN 2

## Slide 3
ROLLOUT SEQUENCE
Four waves create a reversible path to adoption
1
Internal
13 Jul - 31 Jul
2
Pilot
120 workspaces
3
Guided rollout
M-27 gate
4
Review
Q3 close
Internal learning is the only stage without external commitment.
Pilot findings must close before guided rollout opens.
Juniper Works | Product Alpha Q3 | 2026-07-13
PLAN 3

## Slide 4
M-27 CRITERIA
The guided rollout gate requires all five controls
Product quality
No open severity-1 defects; severity-2 mitigation owned
Engineering
Adoption signal
Pilot activation at or above 24% within 14 days
Analytics
Support readiness
Playbook published; on-call coverage confirmed
Support
Comms
Customer notice and FAQ approved
PM + Comms
Rollback
Restore path tested in pilot environment
Release lead
Juniper Works | Product Alpha Q3 | 2026-07-13
PLAN 4

## Slide 5
OPERATING RESPONSE
Every wave has an owner, a signal, and a rollback path
PM: chairs daily command center and records go/no-go evidence.
Engineering: monitors defects, latency, and restores the prior experience if thresholds breach.
Support: routes issue themes, updates macros, and escalates urgent account impact.
Comms: sends staged notices only after the gate evidence is signed.
Juniper Works | Product Alpha Q3 | 2026-07-13
PLAN 5

## Slide 6
DECISION REQUEST
Approve the M-27 readiness plan and pilot entry
Next checkpoint: pilot evidence review on 2026-09-14.
M-27 guided rollout gate: 2026-09-18
Authorize 120-workspace pilot after internal exit review.
Hold guided rollout until every M-27 criterion is evidenced.
Use rollback rather than exception-making when a safety threshold is breached.
Juniper Works | Product Alpha Q3 | 2026-07-13
PLAN 6