## Overview
Dependency control tower
Product Alpha Q3 ¦ Snapshot 2026-07-13 ¦ M-27 guided rollout gate: 2026-09-18
Snapshot | 2026-07-13 | Open dependencies | 22 | Gate | 2026-09-18
Adoption baseline | 18.4% | Blocked | 1 | Gate confidence | 73.14%
Adoption target | 26% | At risk | 5 | Health green | 12
Synthetic workspaces | 1240 | Critical severity | 5 | Due in 14d | 2
Decision frame
The program must raise adoption from 18.4% to 26.0% across 1,240 synthetic workspaces while preserving a 2026-09-18 M-27 gate. Escalate any blocked critical dependency, any confidence below 70%, or any deliverable due within 14 days without a verified mitigation.

## Partner readiness
Partner readiness tracker
Formula-driven days-at-risk and health. Source of truth: Product Alpha Q3 dependency register.
Snapshot date | 2026-07-13
ID | Dependency | Upstream team | Owner role | Status | Due date | Severity | Confidence | Upstream deliverable | Downstream outcome | Mitigation | Workstream | Days at risk | Health
D-01 | SSO metadata confirmation | Platform Identity | Identity Lead | In progress | 2026-07-24 | High | 75% | M-27 pilot enrollment | Tenant invitation | Security review weekly | Identity | 11 | Amber
D-02 | API rate-limit baseline | Core Platform | Platform Architect | In progress | 2026-07-29 | Critical | 65% | Guided rollout API calls | Pilot task completion | Load-test 1,240 synthetic workspaces | Platform | 16 | Amber
D-03 | Event taxonomy v3 | Data Foundations | Analytics PM | At risk | 2026-08-03 | High | 55% | Adoption instrumentation | Weekly adoption scorecard | Freeze v2 mapping and backfill | Analytics | 21 | Amber
D-04 | Consent copy approval | Trust Operations | Privacy Counsel | In progress | 2026-07-31 | Medium | 85% | Invite experience | Pilot activation | Pre-review localized variants | Trust | 18 | Green
D-05 | Lifecycle email templates | Growth Operations | Lifecycle Manager | On track | 2026-08-07 | Medium | 90% | Activation nudges | Adoption lift | Use approved copy modules | Growth | 25 | Green
D-06 | Support runbook training | Customer Experience | Support Enablement | In progress | 2026-08-14 | High | 70% | Guided rollout readiness | Escalation response | Train 18 regional agents | CX | 32 | Green
D-07 | Billing entitlement mapping | Monetization Systems | Billing Product Lead | Blocked | 2026-08-10 | Critical | 40% | Feature access check | Pilot enrollment | Fallback to allowlist for beta | Monetization | 28 | Red
D-08 | Workspace migration dry run | Delivery Engineering | Migration Manager | At risk | 2026-08-17 | High | 60% | Existing customer eligibility | Cohort expansion | Run 100-workspace rehearsal | Delivery | 35 | Amber
D-09 | Accessibility audit | Experience Quality | Accessibility Lead | In progress | 2026-08-21 | Medium | 80% | Release candidate | M-27 gate evidence | Test screen reader flow and keyboard nav | Quality | 39 | Green
D-10 | Partner integration sandbox | Partner Engineering | Partner Manager | At risk | 2026-08-18 | High | 50% | Partner workflow validation | Partner cohort entry | Hold twice-weekly sandbox office hours | Partners | 36 | Amber
D-11 | Security threat assessment | Product Security | Security Architect | On track | 2026-08-12 | Critical | 90% | Release candidate | M-27 gate evidence | Track findings in security triage | Security | 30 | Amber
D-12 | Legal DPA addendum | Commercial Legal | Commercial Counsel | In progress | 2026-08-28 | High | 70% | Enterprise pilot contracts | Enterprise cohort entry | Use standard addendum with redline SLA | Legal | 46 | Green
D-13 | In-app guidance localization | Content Design | Content Strategist | On track | 2026-08-24 | Medium | 88% | International pilot | Activation completion | Prioritize JP and DE critical paths | Content | 42 | Green
D-14 | Experiment flag provisioning | Release Engineering | Release Manager | On track | 2026-08-05 | High | 92% | Cohort controls | Staged rollout | Validate kill switch in preprod | Release | 23 | Green
D-15 | Data retention job validation | Data Infrastructure | Data Steward | In progress | 2026-08-26 | High | 73% | Compliance signoff | M-27 gate evidence | Run retention job against synthetic cohort | Data | 44 | Green
D-16 | Sales enablement brief | Revenue Enablement | Field Enablement Lead | On track | 2026-08-19 | Low | 95% | Field feedback loop | Pipeline visibility | Publish FAQ and objection guide | Revenue | 37 | Green
D-17 | Mobile notification service check | Mobile Platform | Mobile Engineering Lead | At risk | 2026-08-16 | Medium | 58% | Mobile activation | Activation completion | Use email fallback for unsupported devices | Mobile | 34 | Amber
D-18 | Provisioning SLA confirmation | Customer Operations | Operations Lead | In progress | 2026-08-11 | High | 78% | Pilot onboarding | Time-to-value | Measure queue with 48h response target | Operations | 29 | Green
D-19 | Usage export schema | Reporting Platform | Reporting PM | On track | 2026-09-01 | Medium | 86% | Admin reporting | Pilot renewal signal | Ship v1 fields with documented gaps | Reporting | 50 | Green
D-20 | Executive gate packet | Program Management | Program Director | In progress | 2026-09-11 | Critical | 68% | M-27 guided rollout gate | 2026-09-18 gate decision | Refresh evidence every Friday | Program | 60 | Amber
D-21 | Synthetic workspace load test | Quality Engineering | Performance Lead | At risk | 2026-08-09 | Critical | 52% | API baseline | M-27 gate evidence | Simulate 1,240 workspaces with 20% burst | Quality | 27 | Amber
D-22 | Adoption cohort definition | Product Analytics | Insights Lead | On track | 2026-07-27 | High | 89% | 18.4% to 26.0% target | Weekly adoption scorecard | Lock denominator and cohort exclusions | Analytics | 14 | Green

## Partner actions
Partner actions
Role-based follow-up queue. Update status and mitigation in the source register; derived health remains formula-driven.
Escalation trigger | Cadence | Decision owner | Evidence | Next review | Exit condition
Critical blocked dependency | 48 hours | Program Director | Owner recovery plan | 2026-07-15 | Unblock date confirmed
Confidence below 70% | Weekly | Product Manager | Mitigation and dependency map | 2026-07-17 | Confidence at or above 70%
Due in 14 days | Twice weekly | Workstream lead | Readiness checklist | 2026-07-16 | Acceptance evidence attached
Gate evidence incomplete | Friday | Release Manager | M-27 evidence packet | 2026-08-28 | Gate packet accepted
Adoption below weekly path | Monday | Growth Operations | Cohort scorecard | 2026-07-20 | Path to 26.0% restored