## Slide 1
BOARD DECISION BRIEFING
Privacy preservation decision briefing
Approve a time-bound remediation path before the 12 July exception deadline.
Aster Legal / Matter Alpha AL-PA-2606 / 30 Jun 2026

## Slide 2
DECISION REQUIRED
02
The control gap is contained, but the exception must close on schedule
Aster Legal | Matter Alpha AL-PA-2606 | 30 Jun 2026
PRESERVATION UNIVERSE
42
identified in Matter Alpha
COMPLETED
38
preserved and documented
OPEN EXCEPTIONS
4
owner confirmations pending
Board ask
Authorize closure by 12 July with weekly legal escalation.
Endorse owner accountability for the four outstanding exceptions.
Approve a limited contingency review if an exception remains open.

## Slide 3
ASSURANCE PICTURE
03
Four exceptions share one controlled path to closure
Aster Legal | Matter Alpha AL-PA-2606 | 30 Jun 2026
Exception 01
Custodian confirmation; owner: Records Ops
Exception 02
Repository access validation; owner: IT Legal
Exception 03
Retention snapshot; owner: Security Ops
Exception 04
Vendor archive attestation; owner: Privacy Counsel
Closure rule
Each exception closes only when preservation evidence, owner sign-off, and legal review are recorded.
Escalation: 08 Jul • Decision point: 12 Jul

## Slide 4
OPERATING CADENCE
04
A short, auditable cadence protects the legal position
Aster Legal | Matter Alpha AL-PA-2606 | 30 Jun 2026
30 Jun
Board authorization
03 Jul
Evidence review
08 Jul
Escalation gate
12 Jul
Exception deadline
Owners: Privacy Counsel (accountable) • Records Ops, IT Legal, Security Ops (responsible)
Deliverable: closure log with preserved evidence and dated legal approval.

## Slide 5
RESOLUTION
05
Approve the closure path and preserve escalation authority
Aster Legal | Matter Alpha AL-PA-2606 | 30 Jun 2026
Recommended resolution
The Board authorizes management to complete the four controlled exceptions by 12 July 2026, with Privacy Counsel reporting any unresolved exception at the 08 July escalation gate and seeking further direction if closure cannot be substantiated.
Owner: Corporate Privacy Counsel • Next report: 08 Jul 2026