## Slide 1
COMMITTEE READOUT
Privacy Committee readout
Decision record, actions, and evidence status for the June control review.
Aster Legal / Matter Alpha AL-PA-2606 / 30 Jun 2026

## Slide 2
MEETING RECORD
02
The committee accepted the preservation status and set a closure cadence
Aster Legal | Matter Alpha AL-PA-2606 | 30 Jun 2026
Record of discussion
Matter Alpha status: 42 in scope; 38 complete; four controlled exceptions.
No expansion of scope requested at the June meeting.
Committee requested written evidence checkpoints before deadline.
Decision recorded
Maintain legal hold; close exceptions through evidence review; escalate at 08 July if any owner evidence is incomplete.

## Slide 3
ACTION REGISTER
03
Each action has one accountable owner and an objective closure test
Aster Legal | Matter Alpha AL-PA-2606 | 30 Jun 2026
Records Ops
Custodian confirmations
03 Jul
IT Legal
Access validation
05 Jul
Security Ops
Retention snapshot
06 Jul
Privacy Counsel
Vendor archive attestation
08 Jul

## Slide 4
EVIDENCE PATH
04
The committee will review proof of closure, not status assertions
Aster Legal | Matter Alpha AL-PA-2606 | 30 Jun 2026
Preservation evidence
→
Owner sign-off
→
Legal review
→
Closure log
Required standard: dated, attributable evidence that supports continued preservation and defensible exception closure.

## Slide 5
CLOSE-OUT RECORD
05
Committee follow-up is limited, visible, and time-bound
Aster Legal | Matter Alpha AL-PA-2606 | 30 Jun 2026
DEADLINE
12 Jul
exception closure
ESCALATION
08 Jul
if evidence incomplete
ACCOUNTABLE
Counsel
final legal review
Next step: Privacy Counsel circulates the closure log and exception evidence package for committee review.