## Slide 1
METRIC DASHBOARD
Privacy preservation dashboard
A concise operating view for the Matter Alpha legal hold closure window.
Aster Legal / Matter Alpha AL-PA-2606 / 30 Jun 2026

## Slide 2
AT A GLANCE
02
Completion is 90%; exception closure is the only active decision area
Aster Legal | Matter Alpha AL-PA-2606 | 30 Jun 2026
IN SCOPE
42
preservation targets
COMPLETE
38
evidence recorded
OPEN
4
controlled exceptions
DEADLINE
12 Jul
closure target
Status: controlled remediation in progress; no unowned exception.

## Slide 3
COMPLETION TREND
03
The final four items require evidence validation, not volume processing
Aster Legal | Matter Alpha AL-PA-2606 | 30 Jun 2026
Chart: 
| In scope | Complete | Open
Items | 42 | 38 | 4
Interpretation
The completion count is stable. Closure quality depends on documented proof for each exception.

## Slide 4
EXCEPTION OWNERSHIP
04
Four accountable owners are aligned to the closure sequence
Aster Legal | Matter Alpha AL-PA-2606 | 30 Jun 2026
Records Ops
Confirmation
On track
IT Legal
Access
On track
Security Ops
Snapshot
On track
Privacy Counsel
Attestation
On track

## Slide 5
DECISION WINDOW
05
Escalate early if the evidence package is incomplete
Aster Legal | Matter Alpha AL-PA-2606 | 30 Jun 2026
03 Jul
Confirm
05–06 Jul
Validate
08 Jul
Escalate
12 Jul
Close
Owner: Corporate Privacy Counsel | Ask: maintain escalation authority through close-out