Matter Alpha Workplan

Execution workplan

| Matter | As of | Control point |
| --- | --- | --- |
| AL-PA-2606 | 2026-06-30 | Exception deadline: 2026-07-12 |

42 subjects; 38 acknowledgements; 4 pending; 53 sources; 48 ready; 5 exceptions; exception decision deadline 2026-07-12.

# Executive purpose

Coordinate actions through the 2026-07-12 exception deadline.

# Operating facts

42 subjects; 38 acknowledgements; 4 pending; 53 sources; 48 ready; 5 exceptions; exception decision deadline 2026-07-12.

| Metric | Current position | Required action |
| --- | --- | --- |
| Acknowledgements | 38 of 42 | Follow up with 4 pending |
| Sources | 48 of 53 ready | Resolve 5 exceptions |
| Decision date | 2026-07-12 | Record approval or alternate control |

# Milestone calendar

| When | Deliverable | Accountable owner |
| --- | --- | --- |
| 2026-06-30 | Baseline reconciled | Privacy Legal Lead |
| 2026-07-05 | Exception review | Collection Coordinator |
| 2026-07-12 | Decision record complete | Matter lead |

# 1. Milestones and owners

Coordinate actions through the 2026-07-12 exception deadline. This record is a synthetic working document prepared for Aster Legal and is not legal advice, evidence, or a client file.

| Control / question | Owner | Evidence |
| --- | --- | --- |
| Confirm current status | Privacy Legal lead | Dated status note and source reference |
| Apply documented control | Collection coordinator | Control confirmation in working log |
| Escalate variance | Matter lead | Decision record before 2026-07-12 |

# 2. Weekly operating rhythm

Coordinate actions through the 2026-07-12 exception deadline. This record is a synthetic working document prepared for Aster Legal and is not legal advice, evidence, or a client file.

Validate the synthetic intake statement against the source map.

Record an accountable owner and a next review date.

Preserve the reasoning and the closure evidence in the matter working set.

Control note: no actual underlying content is requested or retained by this exemplar.

# 3. Dependencies and decisions

Coordinate actions through the 2026-07-12 exception deadline. This record is a synthetic working document prepared for Aster Legal and is not legal advice, evidence, or a client file.

| Control / question | Owner | Evidence |
| --- | --- | --- |
| Confirm current status | Privacy Legal lead | Dated status note and source reference |
| Apply documented control | Collection coordinator | Control confirmation in working log |
| Escalate variance | Matter lead | Decision record before 2026-07-12 |

# 4. Completion evidence

Coordinate actions through the 2026-07-12 exception deadline. This record is a synthetic working document prepared for Aster Legal and is not legal advice, evidence, or a client file.

Validate the synthetic intake statement against the source map.

Record an accountable owner and a next review date.

Preserve the reasoning and the closure evidence in the matter working set.

Control note: no actual underlying content is requested or retained by this exemplar.

# Approvals and recordkeeping

Decision owner: Privacy Legal Lead. Operational owner: Collection Coordinator. Review cadence: daily through 2026-07-12, then weekly until all exceptions are closed.