MATTER BETA STATUS SUMMARY

Vendor processor privacy review | 24 June 2026

| Matter | AL-PB-2604 |
| --- | --- |
| Processor | Cinder Bay Processing Ltd. |
| Review posture | Open remediation review |
| Record classification | Synthetic internal working record |

# Executive readout

Matter Beta is a bounded synthetic review of Cinder Bay Processing Ltd. as a proposed vendor processor. The review has identified 12 findings: 3 high, 6 medium, and 3 low. No live personal data, credentials, production exports, or privileged materials are held in this record set.

The three high findings are purpose limitation (B-01), access-control review (B-02), and deletion workflow evidence (B-03). Each requires remediation evidence by 15 August 2026.

# Priority actions

Confirm named accountable roles and milestones for B-01 through B-03 by 1 July 2026.

Evaluate submitted high-finding evidence against the acceptance conditions on 15 August 2026.

Track medium updates to 30 September 2026 and low closure notes to 31 October 2026.

# Findings and dates

| ID | Severity | Control topic | Target |
| --- | --- | --- | --- |
| B-01 | High | Purpose limitation | 15 Aug 2026 |
| B-02 | High | Access control | 15 Aug 2026 |
| B-03 | High | Deletion workflow | 15 Aug 2026 |
| B-04 | Medium | Data inventory | 30 Sep 2026 |
| B-05 | Medium | Transfer record | 30 Sep 2026 |
| B-06 | Medium | Incident notice | 30 Sep 2026 |
| B-07 | Medium | Retention schedule | 30 Sep 2026 |
| B-08 | Medium | Training evidence | 30 Sep 2026 |
| B-09 | Medium | Vendor monitoring | 30 Sep 2026 |
| B-10 | Low | Terminology | 31 Oct 2026 |
| B-11 | Low | Record labeling | 31 Oct 2026 |
| B-12 | Low | Contact routing | 31 Oct 2026 |

# Scope and portfolio context

Matter Beta correspondence is limited to AL-PB-2604. Aster Legal maintains separate portfolio context for Matter Alpha: a preservation population of 42 and an exception deadline of 12 July 2026. That reference does not expand Beta scope or alter its remediation dates.

# Decision request

Corporate Privacy Legal should confirm whether the interim B-08 exception request may proceed under its proposed milestone controls, while retaining the 15 August 2026 deadline for all high findings.