## Summary
Cedar Works ¦ Cross-functional March Close RACI
Close completed 2026-04-06 ¦ FY2026 Q1 shared operating view ¦ Currency: JPY millions
KPI | Value |  | Close control | Status
Q1 Revenue | 1842 |  | Close completion | 2026-04-06
Q1 EBITDA | 222 |  | Bridge check | 12.4
Cash variance | -12.4 |  | RACI coverage | 10
Cash variance bridge ¦ unfavorable JPY 12.4m |  |  |  |  | Close operating rhythm
Driver | JPY m | Owner | Escalation |  | Milestone | Accountable | Decision rule
Collections timing | 7.2 | Treasury Analyst | Controller by 12:00 |  | Apr 3: preliminary flash | Controller | Escalate cash variance > JPY 10.0m
Vendor settlement timing | 3.1 | AP Lead | Accounting Lead by 12:00 |  | Apr 4: variance bridge | FP&A Lead | Reconcile drivers to cash view
Payroll and benefits timing | 1.3 | Accounting Lead | Controller by 12:00 |  | Apr 5: review package | Reviewer | Evidence gaps resolved
Other working capital | 0.8 | Department Owner | Controller by 12:00 |  | Apr 6: close complete | Controller | Publish shared close pack

## RACI
Cedar Works ¦ March Close RACI
Roles: Controller (C), Accounting Lead (AL), FP&A Lead (FP), AP Lead (AP), Treasury Analyst (TA), Department Owner (DO), Reviewer (RV)
Milestone | Due | Controller | Accounting Lead | FP&A Lead | AP Lead | Treasury Analyst | Department Owner | Reviewer | Escalation
Lock subledgers | 2026-04-01 | A | R | C | R | I | I | I | Escalate missing cut-off evidence by 15:00
Collect department accruals | 2026-04-02 | A | C | C | I | I | R | I | Escalate unsubmitted accruals by 12:00
Reconcile cash position | 2026-04-02 | A | C | I | I | R | I | I | Escalate variance > JPY 10.0m by 12:00
Prepare preliminary flash | 2026-04-03 | A | R | R | C | C | I | I | Controller sign-off by 17:00
Validate variance bridge | 2026-04-04 | A | C | R | C | R | C | I | Bridge must reconcile to JPY 12.4m
Review close package | 2026-04-05 | A | R | R | C | C | I | R | Resolve evidence gaps before review close
Publish Q1 close | 2026-04-06 | A | R | R | R | R | I | C | Close completed; archive shared pack
Hold owner follow-ups | 2026-04-07 | A | C | C | I | C | R | I | Controller confirms remediation owners
Document control exceptions | 2026-04-08 | A | R | C | C | C | C | R | Reviewer logs exceptions and due dates
Refresh operating forecast | 2026-04-10 | A | C | R | C | C | C | I | FP&A Lead escalates material changes
Q1 town hall | 2026-04-13 | A | C | R | C | C | I | I | Controller facilitates next actions

## Checks
Cedar Works ¦ Close Controls
Control | Expected | Actual | Delta | Status
Cash variance bridge total | 12.4 | 12.4 | 1.7764e-15 | PASS
Collections timing | 7.2 | 7.2 | 0 | PASS
Vendor settlement timing | 3.1 | 3.1 | 0 | PASS
Payroll and benefits timing | 1.3 | 1.3 | 0 | PASS
Other working capital | 0.8 | 0.8 | 0 | PASS
Close date control | Expected | Actual | Delta / Status | Status
Close completion | 2026-04-06 | 2026-04-06 | 0 | PASS
RACI tasks | 11 | 11 | 0 | PASS