## Inputs
2026 Q3 Reliability Runbook Database Failover Analysis Workbook Xlsx
Northstar Transit Cloud ¦ Platform Reliability ¦ p02-full-004649
Metric | Value | Unit
Checkout peak | 2420 | requests/s
Peak demand | 2420 | requests/s
Recovery drain | 1460 | jobs/min
Error allowance remaining | 2.4% | request-error allowance
Identity p95 | 286 | ms below 350 ms
Post-mitigation headroom | 31% | percent
Artifact fingerprint | 1973 | variant
Evidence relationship | rel.inc260713.timeline | contract
Baseline demand | 1850 | requests/s
Peak demand | 2420 | requests/s
Availability SLO | 99.95% | percent
Lowest availability | 92.14% | percent
Scope facts and canonical corpus anchors
Dependency metric | Checkout peak
Dependency source | documents/operations/runbooks/supporting-data/2026-07-14-reliability-runbook-traffic-shift-metrics-tsv-s001098.tsv
Focus | org.ntc · term.mitigation · rel.inc260713.timeline · period.2026-q3
Checkout latency SLO | 99.0% below 400 ms
Canonical corpus anchors | Northstar Transit Cloud ¦ Checkout SVC-17 ¦ 2026-07-13 ¦ error budget 2.4% ¦ INC-260713
Variant | 54

## Timeline
Capacity evidence: exact frozen milestones
UTC | Status | Canonical event
09:18 | DEP start | DEP-260713-017 start
09:42 | Warning | Q-07 warning threshold 12,000
09:47 | S2 | S2 declared
09:54 | Rate limit | Authorizations rate-limited; Identity stayed available
10:02 | Rollback approval | Rollback approval
10:11 | Concurrency | Consumer concurrency increased
10:24 | Recovery | Q-07 below 8,000; short-window burn recovery
10:31 | Impact close | Impact ended
10:42 | Resolution | Resolution; enhanced monitoring 24 hours
Maximum observed Q-07 depth |  | 38420
Q-07 warning threshold |  | 12000
Q-07 critical threshold |  | 24000
Dependency citation |  | documents/operations/runbooks/supporting-data/2026-07-14-reliability-runbook-traffic-shift-metrics-tsv-s001098.tsv
Dependency excerpt |  | Dependency evidence: Checkout peak = 2,420 requests/s; source p02-full-001098, row:canonical-metric.

## Review
capacity review: formula-driven conclusions
Derived measure | Formula result
Queue above critical (38,420 − 24,000) | 14420
Demand increase | 30.81%
Availability gap to SLO | 7.81%
Artifact control ID | p02-full-004649
Decision | Evidence
Concurrency raised | 10:11 UTC
Consumer headroom | 31%
Recovery checkpoint | 10:24 UTC