# Project Alpha - Personal Action Notes

Harbor Build | Project Alpha 2026 | 2026-07-29 | CO-014 | JPY 18,600,000

Use: private working notes for coordination follow-through. This is a synthetic project work copy, not an issued instruction or commercial approval.

# Immediate actions

Reconcile the CO-014 allowance basis against the ceiling-services coordination scope.

Confirm the composite view resolves duct, conduit, cable-tray, and support-zone conflicts.

Separate sequencing assumptions from authorization; retain JPY 18,600,000 as the working review value.

Capture closure evidence in the approved project-control record before external distribution.

# Open coordination items

| Item | Next check | Status |
| --- | --- | --- |
| Duct / conduit interface | Confirm a clear conceptual route in the composite coordination view. | Open |
| Support allowance | Clarify whether supports are inside the CO-014 working value. | Open |
| Constrained sequence | Identify which ceiling zones need first-install planning. | Open |
| Review closure | Log approved response and dated coordination note. | Pending |

# Review boundary

No site access details, issued drawings, personal data, or executable field direction are included. Use the workface reference photo as a visual discussion aid only.