## Slide 1
WEEKLY TEAM COORDINATION
Project Alpha
team coordination
brief
Harbor Build
As of 2026-07-29 18:00 JST
A dated working view for the delivery team
Current focus: integrate the approved CO-014 scope, resolve remaining ceiling-zone interfaces, and protect the August coordination milestone.
CO-014 approved 16:42 JST
JPY 18,600,000
Next team review
2026-08-03 look-ahead
HARBOR BUILD / PROJECT ALPHA 2026
AS OF 2026-07-29 18:00 JST / 01
Notes: [Sources]
Synthetic project-control data. No external assets or external claims.
Portfolio snapshot as of 2026-07-29 18:00 JST; CO-014 approval recorded at 16:42 JST.

## Slide 2
The team can protect the next coordination milestone by closing three interfaces
Portfolio snapshot as of 2026-07-29 18:00 JST; CO-014 approval recorded at 16:42 JST.
This week
• Foundation release sequence confirmed
• CO-014 assumptions aligned in the short-interval plan
• Ceiling-zone conflicts narrowed to three zones
What must happen next
1. Assign an accountable discipline and response date to each remaining zone.
2. Verify CO-014 quantities in the release map before 2026-07-31.
3. Use the action register as the shared evidence trail.
HARBOR BUILD / PROJECT ALPHA 2026
AS OF 2026-07-29 18:00 JST / 02
Notes: [Sources]
Synthetic project-control data. No external assets or external claims.
Portfolio snapshot as of 2026-07-29 18:00 JST; CO-014 approval recorded at 16:42 JST.

## Slide 3
Workstreams are aligned, with MEP and procurement under active watch
Portfolio snapshot as of 2026-07-29 18:00 JST; CO-014 approval recorded at 16:42 JST.
Workstream
Health
This week
Next move
Civil / structure
GREEN
Release sequence confirmed
Issue two-week release map
MEP coordination
AMBER
Three zones remain
Close response log
Procurement
AMBER
CO-014 assumptions aligned
Confirm vendor-ready quantities
Quality / close-out
GREEN
Hold-point checklist standardized
Pilot on first released area
HARBOR BUILD / PROJECT ALPHA 2026
AS OF 2026-07-29 18:00 JST / 03
Notes: [Sources]
Synthetic project-control data. No external assets or external claims.
Portfolio snapshot as of 2026-07-29 18:00 JST; CO-014 approval recorded at 16:42 JST.

## Slide 4
The next seven days turn coordination decisions into field-ready evidence
As of 2026-07-29 18:00 JST; CO-014 approved 16:42 JST.
2026-07-30
Circulate decisions
Publish accountable follow-ups from the coordination huddle.
2026-07-31
Verify release map
Check CO-014 quantities against current interfaces.
2026-08-03
Review look-ahead
Confirm the August milestone and escalation needs.
Decision request
Keep unresolved ceiling-zone interfaces visible in the shared action register until a dated response is accepted.
HARBOR BUILD / PROJECT ALPHA 2026
AS OF 2026-07-29 18:00 JST / 04
Notes: [Sources]
Synthetic project-control data. No external assets or external claims.
Portfolio snapshot as of 2026-07-29 18:00 JST; CO-014 approval recorded at 16:42 JST.