## Action Register
Harbor Build ¦ Project Alpha 2026 - Shared Action Register
Portfolio snapshot as of 2026-07-29 18:00 JST ¦ CO-014 approval recorded at 16:42 JST ¦ JPY 18,600,000
Action ID | Workstream | Action / decision | Owner role | Due date | Status | Priority | Dependency | Evidence / next update | Days to due
AR-017 | MEP coordination | Close accountable response log for three ceiling zones | MEP lead | 2026-07-30 | In Progress | High | Design response log | Post accepted responses to shared register | 1
AR-018 | Procurement | Verify CO-014 quantities against vendor-ready package | Procurement lead | 2026-07-31 | In Progress | High | CO-014 JPY 18,600,000 | Record quantity confirmation and exceptions | 2
AR-019 | Civil / structure | Issue two-week release map | Planning lead | 2026-07-31 | Not Started | Medium | Sequencing confirmation | Publish dated release map | 2
AR-020 | Quality / close-out | Pilot hold-point checklist on first released area | Quality lead | 2026-08-05 | Not Started | Medium | Released area | Add pilot findings to coordination huddle | 7
AR-021 | Project controls | Prepare evidence pack for look-ahead review | Project controls | 2026-08-03 | Not Started | High | Updated action register | Confirm milestone health and escalation needs | 5
Portfolio indicators
Open actions | High priority | Due by 2026-08-03
5 | 3 | 4

## Lists
Status | Priority
Not Started | High
In Progress | Medium
Blocked | Low
Complete