## Lookahead
Project Alpha - 14 Day Working Lookahead
CO-014 working value: JPY 18,600,000 ¦ Review date: 2026-07-29
ID | Start | Finish | Work package | Constraint / handoff | Lead role | Status | Cost exposure (JPY) | Notes
LA-01 | 2026-07-29 | 2026-07-29 | Issue revised laydown markup | RFI-014 sketch comments closed | Project manager | In progress | 1240000 | Brief package leads
LA-02 | 2026-07-29 | 2026-07-30 | Set exclusion controls | Zone labels confirmed | Safety coordinator | Not started | 1980000 | Confirm zone separation
LA-03 | 2026-07-30 | 2026-07-31 | Set materials hold area | Hold-area limits reviewed | Logistics lead | Not started | 2470000 | Waste-skip boundary reviewed
LA-04 | 2026-07-31 | 2026-08-01 | Reset crane exclusion zone | Lift plan briefing complete | Lift supervisor | Not started | 4880000 | Central marked zone
LA-05 | 2026-08-03 | 2026-08-04 | Set concrete pump hold zone | Work-zone control in place | Field lead | Not started | 3110000 | Confirm hold-area limits
LA-06 | 2026-08-05 | 2026-08-06 | Field verification review | All zone checks complete | Project controls | Not started | 3360000 | Record exceptions
LA-07 | 2026-08-07 | 2026-08-11 | Sequence contingency review | Weather and sequencing impacts reviewed | Project manager | Planned | 1560000 | No procurement commitment
Working total | Formula check | CO-014 approved reference | Variance | Release condition | Next review | Owner
18600000 | Matches CO-014 | 18600000 | 0 | Ready for coordination | 2026-07-30 | Project controls

## Assumptions
Working assumptions | Value
Review date | 2026-07-29
CO-014 working value | 18600000
Planning horizon (days) | 14
Project | Project Alpha 2026
Change order | CO-014
Status | Working coordination