## Slide 1
PROJECT ALPHA
Morning huddle: confirm the revised work zones
CO-014 is held at a working value of JPY 18,600,000. The immediate job is consistent exclusion and hold-zone control.
TODAY'S DECISION
Release after exclusion controls, hold-zone marking, and RFI-014 verification.
HARBOR BUILD | PROJECT ALPHA 2026 | 2026-07-29
MORNING HUDDLE 1/3
Notes: [Sources]
Synthetic Project Alpha control data created for this working draft. No external assets or external claims used.
[/Sources]

## Slide 2
The field setup has three non-negotiable controls
Each control is visible, checkable, and owned before activity begins.
1
SEPARATE
Maintain the defined exclusion and hold zones during work-zone coordination.
2
MARK
Set the central crane exclusion zone and concrete pump hold zone to the working markup.
3
VERIFY
Close RFI-014 sketch comments and record the zone-control review before release.
HARBOR BUILD | PROJECT ALPHA 2026 | 2026-07-29
MORNING HUDDLE 2/3
Notes: [Sources]
Synthetic Project Alpha control data created for this working draft. No external assets or external claims used.
[/Sources]

## Slide 3
CO-014 working value is aligned to the current lookahead
Working allocation by field package (JPY millions)
Chart: 
| Temporary works | Crane coordination | Pump relocation | Materials handling | Field verification | Risk allowance
JPY millions | 5.24 | 4.88 | 3.11 | 2.47 | 3.36 | 1.56
RELEASE CHECK
JPY 18,600,000
Confirm commercial exceptions, then record the zone-control review and issue the next coordination update.
HARBOR BUILD | PROJECT ALPHA 2026 | 2026-07-29
MORNING HUDDLE 3/3
Notes: [Sources]
Synthetic Project Alpha control data created for this working draft. No external assets or external claims used.
[/Sources]