## Coding Reference
Harbor Build Coding Structure Reference
Project Alpha 2026 ¦ Control date 2026-07-29 ¦ CO-014 JPY 18,600,000 ¦ Synthetic internal reference
Code | Record family | Example identifier | Required fields | Lifecycle | CO-014 relation | Quality check
RFI | Clarification request | RFI-ALPHA-021 | Question; source; impact; response due | Draft > Issued > Answered > Closed | Reference only if affected | One decision per request
CO | Change evaluation | CO-014 | Baseline; estimate; time; assumptions; disposition | Draft > Reviewed > Approved/Returned | Primary anchor | Visible arithmetic
SUB | Submittal | SUB-2605-07 | Product; section; review state; exception | Draft > Submitted > Reviewed > Closed | Link if scope affected | Source revision present
INSP | Inspection record | INSP-ALPHA-029 | Area; criteria; result; evidence; follow-up | Planned > Observed > Closed | Do not imply release | Disposition recorded
MTG | Meeting action | MTG-ALPHA-014 | Topic; role owner; target; evidence | Open > Verified > Closed | Link interface action | Owner role only
DEV | Deviation log | DEV-018 | Section; exception; disposition; evidence | Open > Review > Resolved | Link change if material | No hidden exception
MOD | Model issue | MOD-COORD-011 | Location; discipline; clash; action | Open > Coordinated > Verified | Model context only | No site access data
CLS | Closeout evidence | CLS-ALPHA-006 | Record set; exception status; acceptance evidence | Assembled > Reviewed > Archived | Reconcile approved value | Evidence retained

## CO-014 Check
CO-014 Arithmetic Check
Illustrative controlled estimate; not an authorization to proceed.
Line | Scope component | Amount (JPY) | Control note
1 | Design coordination | 2400000 | Scoped interface planning
2 | Structural revisions | 3650000 | Connection coordination
3 | MEP reroute | 4180000 | Equipment support coordination
4 | Fire protection | 1760000 | Trade interface
5 | Envelope revisions | 2480000 | Flashing and waterproofing
6 | Commissioning | 1330000 | Testing and controls
7 | General conditions | 2800000 | Controlled recovery support
Reconciled total |  | 18600000 | Expected: JPY 18,600,000
PASS - matches CO-014 anchor