## Overview
Harbor Build ¦ Project Alpha 2026 controls snapshot
Reporting date | 2026-07-29 | Control area | Decision or constraint | Owner role | Due date | Status
Contract change | CO-014 | Commercial | CO-014 decision record | Client commercial lead | 2026-08-05 | AMBER
Proposed value | 18600000 | Programme | Structural release coordination | Design coordination lead | 2026-08-02 | AMBER
Commercial status | AMBER | Controls | Open-items review | Project controls lead | 2026-08-03 | GREEN
Programme status | AMBER
Quality status | GREEN
Control interpretation
Pre-approval control snapshot as of 2026-07-29 12:00 JST. CO-014 is recorded as a proposed JPY 18,600,000 commercial decision; this export is superseded by approval recorded at 16:42 JST and does not authorize field release or work instructions.

## CO-014
CO-014 commercial control build-up
Cost component | Basis | Amount (JPY) | Control status | Share of total
Direct works | Measured scope adjustment and specialist coordination | 12400000 | Reviewed | 66.67%
Preliminaries | Time-related site management allowance | 2100000 | Reviewed | 11.29%
Design coordination | Drawing, model, and interface management | 1600000 | Reviewed | 8.602%
Risk allowance | Defined residual interface exposure | 2500000 | Pending decision | 13.44%
Total proposed CO-014 |  | 18600000 | For approval | 100%
Programme treatment
Pre-approval snapshot as of 2026-07-29 12:00 JST, superseded by approval recorded at 16:42 JST. This control view does not issue a field release. Assessed effect: five working days if decision is deferred beyond the next coordination gate.

## Open Items
Project Alpha open items register
Item ID | Topic | Control owner | Due date | Dependency | Status | Age (days)
OI-071 | CO-014 scope boundary confirmation | Commercial lead | 2026-08-05 | Client decision record | AMBER | 7
OI-072 | Structural release coordination | Design coordination lead | 2026-08-02 | RFI response log | AMBER | 4
OI-073 | Mock-up observation closeout | Quality lead | 2026-08-03 | Photographic evidence | GREEN | 5
OI-074 | Lifting-plan interface review | Work package lead | 2026-08-04 | Sequencing review | GREEN | 6
OI-075 | Procurement interface hold point | Procurement lead | 2026-08-01 | CO-014 decision | AMBER | 3