## Slide 1
HARBOR BUILD / PROJECT ALPHA 2026
Steering export | 2026-07-29
01
Project Alpha
control snapshot
A focused decision view for the July commercial and coordination gate.
CO-014
JPY
18,600,000
Proposed change value
Decision record due 2026-08-05
Notes: [Sources]
Synthetic Project Alpha control data created for this export. No external assets, external claims, real project records, site-access procedures, or field-release instructions are used.
Snapshot status: pre-approval at 2026-07-29 12:00 JST; superseded by approval recorded at 16:42 JST.

## Slide 2
HARBOR BUILD / PROJECT ALPHA 2026
Control posture
02
The project remains controllable;
CO-014 is the decision concentration.
Commercial, programme, quality, and safety are being held through explicit control points.
Commercial
AMBER
Decision record required
Programme
AMBER
Structural release gate
Quality
GREEN
Mock-up evidence closeout
Safety
GREEN
Interface review before release
Notes: [Sources]
Synthetic Project Alpha control data created for this export. No external assets, external claims, real project records, site-access procedures, or field-release instructions are used.
Snapshot status: pre-approval at 2026-07-29 12:00 JST; superseded by approval recorded at 16:42 JST.

## Slide 3
HARBOR BUILD / PROJECT ALPHA 2026
Commercial decision
03
CO-014 is a defined proposal,
not an approved forecast adjustment.
JPY 18,600,000 proposed value
Direct works
12.4m
Preliminaries
2.1m
Design coordination
1.6m
Risk allowance
2.5m
Decision
needed
Scope boundary
Cost and allowance
Programme treatment
Notes: [Sources]
Synthetic Project Alpha control data created for this export. No external assets, external claims, real project records, site-access procedures, or field-release instructions are used.
Snapshot status: pre-approval at 2026-07-29 12:00 JST; superseded by approval recorded at 16:42 JST.

## Slide 4
HARBOR BUILD / PROJECT ALPHA 2026
Next control gates
04
Five open items close within
the next seven days.
08/01
Procurement hold point
AMBER
08/02
Structural release
AMBER
08/03
Open-items review
GREEN
08/04
Interface review
GREEN
08/05
CO-014 decision
AMBER
Control principle: retain affected work under a controlled hold point while releasing unaffected procurement interfaces.
Notes: [Sources]
Synthetic Project Alpha control data created for this export. No external assets, external claims, real project records, site-access procedures, or field-release instructions are used.
Snapshot status: pre-approval at 2026-07-29 12:00 JST; superseded by approval recorded at 16:42 JST.

## Slide 5
HARBOR BUILD / PROJECT ALPHA 2026
Steering close
05
Record the CO-014 decision by
2026-08-05 to protect the next gate.
The steering action is narrow: confirm the scope boundary, the JPY 18,600,000 commercial treatment, and the programme response.
Decision record
Accepted scope, cost, and programme treatment.
Owner roles
Commercial, design coordination, and controls leads.
Evidence base
CO-014 package, RFI log, and open-items register.
Synthetic export: no addresses, access procedures, personal data, or contract instructions included.
Notes: [Sources]
Synthetic Project Alpha control data created for this export. No external assets, external claims, real project records, site-access procedures, or field-release instructions are used.
Snapshot status: pre-approval at 2026-07-29 12:00 JST; superseded by approval recorded at 16:42 JST.