## Submittal Register
HARBOR BUILD ¦ PROJECT ALPHA ¦ INCOMING SUBMITTAL REGISTER
Snapshot date: 2026-07-29 ¦ Coordination reference: CO-014 ¦ Project value context: JPY 18,600,000
Submittal ID | Package | Received | Review status | Discipline | CO reference | Due / action | Notes
SUB-241 | Concrete mix test summary | 2026-07-29 | Accepted | Structure | CO-014 | 2026-07-30 | 28-day results meet design basis
SUB-242 | Steel mill certificate | 2026-07-29 | Under review | Structure | CO-014 | 2026-07-31 | Trace heat details against shop package
SUB-243 | Interior board product data | 2026-07-29 | Revise and resubmit | Architecture | CO-014 | 2026-08-03 | Confirm rated opening condition
SUB-244 | Drawing markup coordination | 2026-07-29 | Pending consultant | Coordination | CO-014 | 2026-08-01 | Opening location requires written response
SUB-245 | Level 02 model export | 2026-07-29 | Accepted with notes | BIM | CO-014 | 2026-08-02 | Use as coordination reference only
Summary | Count
Accepted / accepted with notes | 2
Under review | 1
Action required | 2
Total incoming | 5