## Slide 1
SITE COORDINATION
HARBOR BUILD / 01
Project Alpha 2026
Weekly site coordination meeting
29 July 2026 | Harbor Build | Readiness, interfaces, actions
ON SITE
THIS WEEK
Project Alpha 2026 | Internal coordination material | Synthetic
Notes: [Sources]
All project facts, figures, and schedules in this deck are synthetic Harbor Build meeting material. No external assets or non-trivial external claims used.

## Slide 2
PROGRESS EVIDENCE
HARBOR BUILD / 02
Structure release is ahead of envelope readiness
The next constraint is the handoff between facade closures and MEP rough-in.
82%
Structure
64%
Envelope
48%
MEP rough-in
18%
Interiors
Synthetic progress measure | Percent complete reflects planned workface release
Notes: [Sources]
All project facts, figures, and schedules in this deck are synthetic Harbor Build meeting material. No external assets or non-trivial external claims used.

## Slide 3
DECISION REGISTER
HARBOR BUILD / 03
Four interface decisions need owners
Each owner confirms the next observable action before the next site walk.
Facade edge
Confirm sill flashing mock-up by 31 Jul - Design Lead
Level 03 MEP
Release ceiling zone conflict log by 30 Jul - MEP Lead
Material flow
Approve north hoist window adjustment - Site Lead
Quality walk
Close six punch items before Friday walk - Trade Leads
Synthetic internal working record | Harbor Build
Notes: [Sources]
All project facts, figures, and schedules in this deck are synthetic Harbor Build meeting material. No external assets or non-trivial external claims used.

## Slide 4
SEQUENCE
HARBOR BUILD / 04
The two-week path protects the Level 03 handoff
No access details are included; milestones are coordination controls only.
29 Jul
Confirm interfaces
31 Jul
Mock-up review
04 Aug
MEP release
07 Aug
Envelope close
12 Aug
Level 03 handoff
Project Alpha 2026 | Lookahead basis: synthetic field plan
Notes: [Sources]
All project facts, figures, and schedules in this deck are synthetic Harbor Build meeting material. No external assets or non-trivial external claims used.

## Slide 5
DECISION REGISTER
HARBOR BUILD / 05
Meeting closes with a clear control point
Each owner confirms the next observable action before the next site walk.
By 30 Jul
Publish resolved coordination log - PM
By 31 Jul
Record mock-up disposition - Design Lead
By 04 Aug
Verify material routing window - Site Lead
Next meeting
Review Level 03 handoff readiness - All leads
Synthetic internal working record | Harbor Build
Notes: [Sources]
All project facts, figures, and schedules in this deck are synthetic Harbor Build meeting material. No external assets or non-trivial external claims used.