## Slide 1
CHANGE REVIEW
HARBOR BUILD / 01
CO-014
Change review meeting
Project Alpha 2026 | 29 July 2026 | Proposed value: JPY 18,600,000
DECISION
PACKAGE
Synthetic Harbor Build change-control material
Notes: [Sources]
All project facts, figures, and schedules in this deck are synthetic Harbor Build meeting material. No external assets or non-trivial external claims used.

## Slide 2
CHANGE BASIS
HARBOR BUILD / 02
CO-014 consolidates three coordinated impacts
Scope is framed for meeting review; all quantities and costs are synthetic.
Facade interface
Revised edge detailing at two transition zones
MEP routing
Additional support coordination at Level 03
Sequence protection
Resequence closures to preserve planned handoff
CO-014 | Project Alpha 2026
Notes: [Sources]
All project facts, figures, and schedules in this deck are synthetic Harbor Build meeting material. No external assets or non-trivial external claims used.

## Slide 3
PROGRESS EVIDENCE
HARBOR BUILD / 03
JPY 18.6M is concentrated in field interfaces
Share of proposed value; values sum to 100%.
21%
Detailing
46%
Support work
33%
Resequence
Synthetic progress measure | Percent complete reflects planned workface release
Notes: [Sources]
All project facts, figures, and schedules in this deck are synthetic Harbor Build meeting material. No external assets or non-trivial external claims used.

## Slide 4
DECISION PATH
HARBOR BUILD / 04
Approval can proceed with three recorded conditions
Conditions protect traceability without delaying procurement planning.
29 Jul
Review basis
30 Jul
Confirm quantities
31 Jul
Approve conditions
03 Aug
Issue instruction
CO-014 | Synthetic approval workflow
Notes: [Sources]
All project facts, figures, and schedules in this deck are synthetic Harbor Build meeting material. No external assets or non-trivial external claims used.

## Slide 5
DECISION REGISTER
HARBOR BUILD / 05
Approve CO-014 with three conditions
Each owner confirms the next observable action before the next site walk.
Commercial
Accept JPY 18,600,000 ceiling - Commercial Lead
Technical
Attach reviewed transition detail - Design Lead
Planning
Publish revised sequence note - Planner
Record
Issue CO-014 decision log - Project Manager
Synthetic internal working record | Harbor Build
Notes: [Sources]
All project facts, figures, and schedules in this deck are synthetic Harbor Build meeting material. No external assets or non-trivial external claims used.