## Slide 1
TWO-WEEK LOOKAHEAD
HARBOR BUILD / 01
Project Alpha 2026
Two-week field lookahead
29 July - 12 August 2026 | Focus: Level 03 handoff
14 DAY
WINDOW
Synthetic lookahead for coordination discussion
Notes: [Sources]
All project facts, figures, and schedules in this deck are synthetic Harbor Build meeting material. No external assets or non-trivial external claims used.

## Slide 2
MILESTONES
HARBOR BUILD / 02
Five milestones define the handoff path
Sequence confirms readiness, not site-access instructions.
29 Jul
Interfaces
31 Jul
Mock-up
04 Aug
MEP release
07 Aug
Closure
12 Aug
Handoff
Project Alpha 2026 | Synthetic planning controls
Notes: [Sources]
All project facts, figures, and schedules in this deck are synthetic Harbor Build meeting material. No external assets or non-trivial external claims used.

## Slide 3
DECISION REGISTER
HARBOR BUILD / 03
Constraint removal is front-loaded
Each owner confirms the next observable action before the next site walk.
By 30 Jul
Resolve ceiling-zone conflict log - MEP Lead
By 31 Jul
Disposition facade mock-up - Design Lead
By 03 Aug
Confirm material delivery sequence - Site Lead
By 05 Aug
Verify inspections are sequenced - Quality Lead
Synthetic internal working record | Harbor Build
Notes: [Sources]
All project facts, figures, and schedules in this deck are synthetic Harbor Build meeting material. No external assets or non-trivial external claims used.

## Slide 4
PROGRESS EVIDENCE
HARBOR BUILD / 04
Workface readiness rises as constraints close
Readiness index is a synthetic coordination measure.
42%
29 Jul
58%
31 Jul
71%
04 Aug
84%
07 Aug
92%
12 Aug
Synthetic progress measure | Percent complete reflects planned workface release
Notes: [Sources]
All project facts, figures, and schedules in this deck are synthetic Harbor Build meeting material. No external assets or non-trivial external claims used.

## Slide 5
DECISION REGISTER
HARBOR BUILD / 05
Escalate only the issues that threaten 12 August
Each owner confirms the next observable action before the next site walk.
Escalation trigger
Unresolved facade mock-up after 31 Jul - PM
Escalation trigger
MEP conflict open after 04 Aug - MEP Lead
Control
Daily 15-minute constraint review - Trade Leads
Next review
Validate handoff checklist on 05 Aug - All leads
Synthetic internal working record | Harbor Build
Notes: [Sources]
All project facts, figures, and schedules in this deck are synthetic Harbor Build meeting material. No external assets or non-trivial external claims used.