# Project Alpha 2026
Action Item Minutes

Site coordination meeting | 29 July 2026 | Harbor Build | Prepared as synthetic meeting material

# Meeting outcome

The team aligned the Level 03 handoff around facade closure readiness, a resolved MEP routing log, and a short set of traceable decisions. CO-014 was reviewed at JPY 18,600,000 with conditions to be captured in the change record.

# Action register

| Action | Owner | Due | Success check |
| --- | --- | --- | --- |
| Resolve Level 03 ceiling-zone conflicts | MEP Lead | 30 Jul | Updated log records no open coordination clash. |
| Record facade mock-up disposition | Design Lead | 31 Jul | Approved or revised detail attached to record. |
| Issue CO-014 decision record | Project Manager | 31 Jul | Conditions and JPY 18,600,000 value stated. |
| Verify material-flow coordination note | Site Lead | 03 Aug | Updated routing note is ready for field review. |
| Validate handoff readiness | All Leads | 05 Aug | Closure, MEP release, and quality actions confirmed. |

# Control notes

The 12 August handoff remains the common coordination control point.

Escalate an unresolved facade disposition after 31 July or an unresolved MEP log after 04 August.

No access instructions, personal data, credentials, or confidential drawings are retained in this record.

# Next meeting

05 August 2026: review the handoff checklist, confirm completed actions, and identify only issues that could affect the 12 August handoff.