## Cost Breakdown
Harbor Build ¦ Project Alpha 2026 ¦ CO-014 ¦ Line-item cost breakdown
Status date | 2026-07-29 | Control status | Pending approval
Line | Scope line | Cost class | Amount (JPY)
1 | CO-014 Design coordination and revised access sequencing | Labor | 2400000
2 | CO-014 Structural steel connection revisions | Material | 3650000
3 | CO-014 MEP reroute and equipment supports | Labor | 4180000
4 | CO-014 Fire protection coordination changes | Labor | 1760000
5 | CO-014 Envelope flashing and waterproofing revisions | Material | 2480000
6 | CO-014 Controls commissioning and testing | Labor | 1330000
7 | CO-014 General conditions and schedule recovery | General conditions | 2800000
CO-014 reconciled total |  |  | 18600000
Pre-approval control snapshot — as of 2026-07-29 15:30 JST; superseded by approval recorded at 16:42 JST. Before approval, release was prohibited.