## Change Register
Project Alpha Change Order Register
Harbor Build ¦ Status at 2026-07-29 | Harbor Build ¦ Status at 2026-07-29 | Harbor Build ¦ Status at 2026-07-29 | Harbor Build ¦ Status at 2026-07-29 | Harbor Build ¦ Status at 2026-07-29 | Harbor Build ¦ Status at 2026-07-29 | Harbor Build ¦ Status at 2026-07-29 | Harbor Build ¦ Status at 2026-07-29
Event | Date | Change order | Scope | Owner | Status | Proposed JPY | Approved JPY
CE-009 | 2026-05-14 | CO-009 | Foundation access revision | Project Controls | Approved | 3200000 | 3200000
CE-011 | 2026-06-03 | CO-011 | Electrical containment adjustment | MEP Lead | Approved | 4750000 | 4500000
CE-012 | 2026-06-21 | CO-012 | Façade mock-up revision | Envelope Lead | Withdrawn | 1100000 | 0
CE-014 | 2026-07-11 | CO-014 | Issued coordination delta | Commercial Controls | Pending approval | 18600000 | 0
CE-015 | 2026-07-26 | CO-015 | Look-ahead resequencing | Project Controls | Under review | 2100000 | 0

## Summary
Change Control Summary ¦ Project Alpha 2026
Metric | Value
Proposed pipeline | 29750000
Approved value | 7700000
CO-014 proposed value | 18600000
Pre-approval control snapshot — as of 2026-07-29 15:30 JST; superseded by approval recorded at 16:42 JST. Before approval, release was prohibited.