## Labor
CO-014 Labor Analysis
Harbor Build ¦ CO-014 ¦ Rates and extended values | Harbor Build ¦ CO-014 ¦ Rates and extended values | Harbor Build ¦ CO-014 ¦ Rates and extended values | Harbor Build ¦ CO-014 ¦ Rates and extended values | Harbor Build ¦ CO-014 ¦ Rates and extended values | Harbor Build ¦ CO-014 ¦ Rates and extended values | Harbor Build ¦ CO-014 ¦ Rates and extended values | Harbor Build ¦ CO-014 ¦ Rates and extended values
Work package | Trade | Hours | Rate JPY/hr | Extended JPY
Design coordination | PM / Engineering | 2400 | 1700 | 4080000
MEP reroute | Installation crew | 7640 | 500 | 3820000
Fire protection coordination | Fire trade | 1800 | 600 | 1080000
Commissioning and testing | Controls trade | 3400 | 300 | 1020000

## Material
CO-014 Material Analysis
Harbor Build ¦ CO-014 ¦ Quantities and unit costs | Harbor Build ¦ CO-014 ¦ Quantities and unit costs | Harbor Build ¦ CO-014 ¦ Quantities and unit costs | Harbor Build ¦ CO-014 ¦ Quantities and unit costs | Harbor Build ¦ CO-014 ¦ Quantities and unit costs | Harbor Build ¦ CO-014 ¦ Quantities and unit costs | Harbor Build ¦ CO-014 ¦ Quantities and unit costs | Harbor Build ¦ CO-014 ¦ Quantities and unit costs
Material package | Unit | Quantity | Unit cost JPY | Material JPY
Structural steel connections | tonne | 150 | 14000 | 2100000
Envelope flashing and waterproofing | m2 | 6200 | 400 | 2480000
Equipment supports and misc. | set | 250 | 4880 | 1220000

## Reconciliation
CO-014 Cost-Class Reconciliation
Cost class | Source | Formula amount | Target JPY
Labor | Labor sheet | 10000000
Material | Material sheet | 5800000
General conditions | Controlled allowance | 2800000 | 2800000
CO-014 total | Formula total | 18600000 | 18600000
Pre-approval control snapshot — as of 2026-07-29 15:30 JST; superseded by approval recorded at 16:42 JST. Before approval, release was prohibited.