## Forecast Dashboard
Project Alpha 2026 ¦ CO-014 Forecast Impact Dashboard
Metric | Baseline JPY | Current approved JPY | CO-014 JPY | Forecast JPY | Decision gate
Construction budget | 420000000 | 412500000 | 18600000 | 431100000 | Approve CO-014
Contingency | 31500000 | 27400000 | 0 | 8800000 | Protect reserve
Contingency remaining | 0 | 0 | 0 | 8800000 | Confirm authorization
Schedule impact (days) | 0 | 0 | 12 | 12 | Access sequence approval
Decision: approve CO-014 at JPY 18,600,000 to maintain the revised access sequence; forecast shows contingency remaining of JPY 8,800,000.
Pre-approval control snapshot — as of 2026-07-29 15:30 JST; superseded by approval recorded at 16:42 JST. Before approval, release was prohibited.

## Assumptions
Forecast Assumptions and Controls
Assumption | Value | Status | Control
CO-014 status | Pending approval | Open | Formal authorization required
Status date | 2026-07-29 | Current | Review at next control gate
Schedule basis | 12 calendar days | Controlled | Maintain revised access sequence