## Drawing Register
HARBOR BUILD - PROJECT ALPHA 2026 DRAWING REGISTER | [7 empty] | CONTROL SUMMARY
Status date: 2026-07-29 ¦ Change Order CO-014 ¦ Approved value: JPY 18,600,000 | [7 empty] | Registered sheets | 5
Post-approval control snapshot as of 2026-07-29 17:50 JST; approval recorded at 16:42 JST | [7 empty] | IFC sheets | 5
Drawing | Title | Discipline | Revision | Issue date | Review state | As-built state | Control note | Pending as-built | 0
A-101 | Level 01 Grid Plan | Architectural | C | 2026-07-29 | Issued for construction | Pending field confirmation | Grid basis | CO-014 value | 18600000
S-201 | Foundation Layout | Structural | C | 2026-07-29 | Issued for construction | Markup incorporated | CO-014 hold point
C-220 | Level 02 Coordination Overlay | Coordination | C | 2026-07-29 | Issued for construction | Coordination complete | MEP clearance
A-401 | East Elevation | Architectural | B | 2026-07-29 | Issued for construction | Pending facade verification | Datum annotation
L-001 | Crane Logistics Plan | Logistics | C | 2026-07-29 | Issued for construction | Historical reference | Planning aid