# RFI-014 - Foundation sleeve coordination

REQUEST FOR INFORMATION | Harbor Build | Project Alpha 2026

| RFI | RFI-014 |
| --- | --- |
| Issued | 2026-07-29 |
| Status | Answered |
| Related change | CO-014 ¦ JPY 18,600,000 context allowance |

# Question

The planned 200 mm service sleeve intersects the local reinforcing cage at the north foundation wall. Confirm a permitted relocation before placement.

# Designer response / coordination direction

Relocate the sleeve centerline 75 mm east. Preserve 40 mm minimum clear cover, do not cut reinforcing, and provide a non-shrink annular grout detail after service installation.

# Schedule and cost review

The direction avoids a concrete placement hold. The work remains within the CO-014 coordination allowance of JPY 18,600,000; no separate change value is authorized.

# Required follow-up

Field team to mark revised centerline before concrete inspection.

Structural coordination to record the sleeve location on the next field-set drawing.

Close RFI after photo verification and inspection note.

## Distribution

Project controls, field supervision, structural coordination, and design review. Synthetic record; no site access or external contacts are included.