# RFI-018 - Level 02 embed plate

REQUEST FOR INFORMATION | Harbor Build | Project Alpha 2026

| RFI | RFI-018 |
| --- | --- |
| Issued | 2026-07-29 |
| Status | Answered |
| Related change | CO-014 ¦ JPY 18,600,000 context allowance |

# Question

The Level 02 embed plate setout conflicts with the beam web tolerance zone. Confirm plate orientation and shimming limits.

# Designer response / coordination direction

Use plate PL-18A rotated 90 degrees with a 12 mm maximum shim pack. Weld preparation is to occur only after survey verification of the final elevation.

# Schedule and cost review

The response protects the steel erection sequence. It is a design clarification and does not revise the CO-014 JPY 18,600,000 allowance.

# Required follow-up

Survey the supporting beam elevation and record actuals.

Install shim pack within the 12 mm limit.

Submit closure photo with plate tag and measured elevation.

## Distribution

Project controls, field supervision, structural coordination, and design review. Synthetic record; no site access or external contacts are included.