# RFI-021 — Roof drain offset

REQUEST FOR INFORMATION | Harbor Build | Project Alpha 2026

| RFI | RFI-021 |
| --- | --- |
| Issued | 2026-07-29 |
| Status | Open - designer confirmation required |
| Related change | CO-014 ¦ JPY 18,600,000 context allowance |

# Question

The roof drain centerline lands within the structural curb clearance zone. Confirm whether a 450 mm offset is acceptable while maintaining slope and membrane detailing.

# Designer response / coordination direction

Proposed field coordination direction is a 450 mm offset away from the curb, pending designer confirmation. Maintain positive drainage, coordinate flashing transitions, and do not begin final membrane work until written closure.

# Schedule and cost review

This remains an open high-priority item because roofing sequence is affected. CO-014 and its JPY 18,600,000 context allowance are not changed by this RFI.

# Required follow-up

Designer to confirm 450 mm offset and flashing detail.

Roofing lead to hold final membrane at the affected bay.

Update RFI log within one working day of response.

## Distribution

Project controls, field supervision, structural coordination, and design review. Synthetic record; no site access or external contacts are included.