## Dashboard
PROJECT ALPHA 2026 ¦ RFI AGING DASHBOARD
As of | 2026-07-29
Open RFIs | 3 | High priority | 1
Aging band | Count
0-3 days | 2
4-7 days | 1
Over 7 days | 0

## RFI Data
RFI DATA INPUTS
RFI | Subject | Issued | Due | Status | Priority | Age Days | Direction | CO Context | Close
RFI-014 | Foundation sleeve coordination | 2026-07-20 | 2026-07-24 | Answered | High | 9 | Approved relocate sleeve 75 mm east; maintain reinforcing clearances. | CO-014 ¦ JPY 18,600,000 | Yes
RFI-018 | Level 02 embed plate | 2026-07-22 | 2026-07-29 | Answered | Medium | 7 | Use PL-18A with 12 mm shim pack; revise field setout. | CO-014 ¦ JPY 18,600,000 | Yes
RFI-021 | Roof drain offset | 2026-07-24 | 2026-07-31 | Open | High | 5 | Designer confirmation requested for 450 mm drain offset. | CO-014 ¦ JPY 18,600,000 | No
RFI-023 | Stair landing edge angle | 2026-07-27 | 2026-08-03 | Open | Medium | 2 | Coordinate edge angle with guard post base plate. | CO-014 ¦ JPY 18,600,000 | No
RFI-026 | Electrical riser firestop | 2026-07-28 | 2026-08-04 | Open | Low | 1 | Awaiting rated assembly selection. | CO-014 ¦ JPY 18,600,000 | No