## Daily Register
Project Alpha 2026 ¦ Daily Site Report Register
Harbor Build ¦ Reporting date: 2026-07-29 ¦ Internal synthetic record
Report date | Report ID | Workface | Weather / condition | Safety status | Progress status | Open actions | Reference
2026-07-27 | DAR-2026-0727 | Central bay | Light cloud; dry | Closed | Reinforcement closeout | Confirm pump setup | Daily report scan
2026-07-28 | DAR-2026-0728 | Central bay / east elevation | Overcast; stable | Closed | 68 m3 placed; panels staged | Verify curing cover | Daily report scan
2026-07-29 | DAR-2026-0729 | Site logistics | Overcast; dry | Closed | Walkdown complete | Recheck morning separation | Daily site report
Summary metric | Value | Formula / basis | Note
Reports logged | 3 | 3 | Daily reports in register
Closed safety checks | 3 | 3 | No open safety hold points
Concrete placed (m3) | 68 | Manual field quantity | 2026-07-28 central bay
CO-014 context (JPY) | 18600000 | Commercial reference only | Not a daily production measure