## Compliance Matrix
Project Alpha Specification Compliance Matrix
Harbor Build ¦ Issued 2026-07-29 ¦ CO-014 ¦ JPY 18,600,000
Section | Requirement | Evidence | Status | CO-014 Impact | Score
03 30 00 | Concrete curing plan submitted | SUB-0330-04 | Compliant | Monitor sequence | 100
05 12 00 | Steel coating touch-up recorded | DEV-018 | Pending | None | 0
07 21 00 | Thermal values confirmed | SUB-0721-02 | Compliant | Sequence only | 100
09 29 00 | Finish level verified | CL-023 | Open | None | 0
23 05 00 | Equipment coordination checked | M-COORD-11 | Compliant | None | 100
26 05 00 | Sleeve routing tracked | DEV-019 | Compliant | Coordination | 100
Portfolio controls |  |  |  | Calculated checks
Control | Value |  |  | Metric | Result
Issue date | 2026-07-29 |  |  | Average compliance | 66.6667
Change order | CO-014 |  |  | Compliant sections | 4
Controlled value (JPY) | 18600000 |  |  | Open / pending | 2

## Control Summary
Project Alpha Specification Control Summary
Harbor Build ¦ Coordination readiness for issued 2026-07-29 package
Control | Value
Issue date | 2026-07-29
CO-014 value (JPY) | 18600000
Average compliance | 66.6667
Open / pending items | 2
Review note: procurement release requires evidence for DEV-018 and closure of CL-023.