## Register
Project Alpha - Submittal Register
Harbor Build ¦ 2026-07-29 ¦ CO-014 controlled packages ¦ JPY 18,600,000 reference
Submittal ID | Spec section | Package | Revision | Received | Status | Reviewer | Due date | CO-014 | Action
033000-07 | 033000 | Concrete Mix Design | 02 | 2026-07-22 | Approved as noted | Project controls | 2026-08-03 | Yes | Add 56-day data
051200-03 | 051200 | Steel Shop Drawings | 01 | 2026-07-21 | Approved as noted | Structural review | 2026-08-03 | Yes | Confirm embeds
072100-02 | 072100 | Insulation Product Data | 03 | 2026-07-18 | Overdue | Envelope review | 2026-07-27 | No | Revise vapor detail
230500-04 | 230500 | HVAC Equipment Data | 01 | 2026-07-23 | Approved | MEP review | 2026-07-30 | Yes | File final data
260500-06 | 260500 | Panelboard Data | 02 | 2026-07-22 | Approved as noted | Electrical review | 2026-08-02 | Yes | Verify labels

## Summary
Submittal Control Summary
Formula-driven count of Project Alpha status as at 2026-07-29
KPI | Value | Control point | Status
Total active | 5 | CO-014 reference | JPY 18,600,000
Approved | 1 | Next review | 2026-08-03
Approved as noted | 3 | Overdue owner | Envelope review
Overdue | 1 | Decision | Escalate attachments