## Approvals
Project Alpha - Material Approval Tracker
Harbor Build ¦ 2026-07-29 ¦ procurement control supporting CO-014
Material ID | Material | Trade | Submittal | Supplier lead days | Required on site | Approval status | Risk | Budget impact JPY | Committed JPY | Variance JPY
MAT-033 | Concrete mix | Concrete | 033000-07 | 14 | 2026-08-17 | Approved as noted | Medium | 4200000 | 4000000 | 200000
MAT-051 | Steel embeds | Structural | 051200-03 | 21 | 2026-08-24 | Approved as noted | High | 6100000 | 6100000 | 0
MAT-072 | Roof insulation | Envelope | 072100-02 | 18 | 2026-08-14 | Overdue | High | 2500000 | 0 | 2500000
MAT-230 | Air handling unit | Mechanical | 230500-04 | 35 | 2026-09-10 | Approved | Medium | 3100000 | 3100000 | 0
MAT-260 | Panelboard | Electrical | 260500-06 | 28 | 2026-09-03 | Approved as noted | Medium | 2700000 | 2500000 | 200000

## Dashboard
Material Approval Dashboard
Live formulas linked to the approvals tracker
KPI | Value | CO-014 control | Current state
Total budget | 18600000 | Allowance reference | 18600000
Committed | 15700000 | Insulation release | Blocked by overdue review
Open variance | 2900000 | Steel embeds | Closeout by 2026-08-03
High risk items | 2