## Drawing Register
Harbor Build - Project Beta Drawing Register
Design phase ¦ Status date: 2026-07-29 ¦ Synthetic portfolio record ¦ Project Alpha CO-014 is not a Project Beta cost authorization
Drawings | Open issues | Preliminary issue | Status date
4 | 3 | 1 | 2026-07-29
Issue Date | 2026-07-29
Sheet No. | Title | Discipline | Revision | Issue Date | Issue Purpose | File | Status | Coordination note
A1.10 | Ground Floor Plan | Architectural | P1 | 2026-07-29 | Preliminary coordination | 00-project-beta-ground-floor-plan-scan.png | Preliminary | Confirm entry canopy extent and accessible route note.
S1.02 | Foundation Layout | Structural | P1 | 2026-07-29 | Preliminary coordination | 01-project-beta-foundation-layout-markup.png | Open | Verify pier alignment at Grid C and service trench depth.
A1.41 | Roof Coordination | Architectural / MEP | P1 | 2026-07-29 | Preliminary coordination | 02-project-beta-roof-plan-coordination-overlay.png | Open | Clear MEP route at curbs; confirm slope to drain.
A3.20 | West Elevation | Architectural | P1 | 2026-07-29 | Preliminary coordination | 03-project-beta-west-elevation-field-annotation.png | Open | Align siding at sill; confirm canopy soffit material.
Formulas:
Status date = [Open issues, row below]

## Issues
Project Beta - Drawing Coordination Issues
Issue ID | Drawing | Observation | Discipline | Status | Opened | Days Open
PB-DRW-01 | S1.02 | Confirm pier alignment and service-trench depth. | Structural / Civil | Open | 2026-07-29 | 0
PB-DRW-02 | A1.41 | Verify curb clearance and roof slope-to-drain continuity. | Architectural / MEP | Open | 2026-07-29 | 0
PB-DRW-03 | A3.20 | Align siding at sill and confirm canopy soffit material. | Architectural | Open | 2026-07-29 | 0
PB-DRW-04 | A1.10 | Confirm entry canopy extent and accessible route note. | Architectural | Open | 2026-07-29 | 0